## Version Details
DOCUMENT VERSIONING DETAILS
Document Name | PEA_Change Request Form
Project Name | Professional Evaluation Application (PEA)
Project Code | PEA_Ext_431
Version Number | Change Description | Created/Modified by | Approved by | Date
0.1 | First draft of the Request for change form | Robin Gupta |  | 2022-01-26
0.2 | Updated the document with the effort and cost details | Robin Gupta |  | 2022-01-27

## Request For Change Form
CHANGE REQUEST (CR) FORM
Project Name | Professional Evaluation Application (PEA) |  |  | RFC Number | PEA_RFC_01
Raised By | Robin G |  |  | Raised On
On behalf of | Acme Corp. |  |  | Severity | High
Request Title | Functionality for the candidate to capture a self snapshot before attempting the assessment
Reason for Change |  | Change Description |  | Change Impact Analysis |  | Impacted Project Artefacts
As per the current implementation, the candidate, while attempting the assessment, is not furnishing any proof of his identity and, there are chances that some other person might attempt the assessment on behalf of the actual candidate. |  | The system should carry out the following changes to prevent unscrupulous activities: 1. While sending the assessment invitation, add a note that devices with cameras should be used for taking the assessment. 2. Append an additional step for the candidate to capture a self snapshot through the device camera/webcam before attempting the assessment - this is a mandatory step 3. The Recruitment and Supervisor should be able to view the snapshot uploaded by the candidate |  | This change can only be introduced in a new sprint and will require coding the respective functionality. Also, the existing impacted areas are: 1. Candidate Flow 2. Database table structure against the candidate 3. Recruitment - Manage candidate flow 4. Administrator - Manage candidate flow |  | 1. Business Requirement Document (BRD) 2. Functionality Matrix (FM) 3. Requirement Traceability Matrix (RTM) 4. User stories against Candidate Flow, Recruitment - Manage candidate flow and Supervisor - Manage candidate flow 5. Test cases against Candidate Flow, Recruitment - Manage candidate flow and Supervisor - Manage candidate flow 6. Architectural Design Document (ADD) 7. Application Data Model
Change Risk Profile | Medium | Implementation Effort | 75 man-hours | Change Authorization Date |  | Change Verified | No
CR Status | Under Discussion | Implementation Cost | 2350 | Change Implementation Date |  | Change Tested | No
|  |  |  | Change Request Closure Date |  | Change Accepted | No