## Version Details
DOCUMENT VERSIONING DETAILS
Document Name | PEA_Ext_431_31Jan_Meeting Details
Project Name | Professional Evaluation Application
Project Code | PEA_Ext_431
Version Number | Change Description | Created/Modified by | Date
1 | Captured details for the meeting held on 31 Jan 2022 | Robin G | 2022-01-31
1.1 | Updated the status of the action items | Robin G | 2022-02-01
Note on B8: Contains the versioning details of the document
Note on C8: Contains details of whether the information was added, deleted or modified in the document
Note on E8: Contains the full name of the user who created, updated or modified the details
Note on F8: Contains the date on which the details were approved. However, if the information is yet to be approved, it should contain the date on which information was created/modified

## Meeting Agenda
MEETING AGENDA
Project Name | Professional Evaluation Application (PEA) |  |  | Customer |  | Acme Corp.
Meeting Title | Requirement Clarification Discussion |  |  | Meeting Date and Time |  | Monday, 31 Jan 2022 10:30 AM EST
Meeting Duration | 60 Minutes |  |  | Venue |  | Online/WebEx
Meeting Objective
The development team would like to clarify the requirements and features of the 'Add new assessment' functionality against the Evaluation Panel module.
Agenda No. | Agenda/Action Item Description |  | Desired Outcome |  | Presenter |  | Time allowed | Notes
1 | Which roles are supposed to have the permission to create a new assessment and are those permissions transferrable? |  | Permissions listing |  | Robin G |  | NA | Details not available in BRD and SRS documents
2 | Walkthrough and confirmation of features against Assessment Instructions |  | Confirmation from the business |  | Robin G |  | NA
3 | Walkthrough and confirmation of features against Assessment Settings |  | Confirmation from the business |  | Robin G |  | NA
4 | Walkthrough and confirmation of features against Assessment Sections |  | Confirmation from the business |  | Robin G |  | NA
5 | Walkthrough and confirmation of features against Assessment Questions |  | Confirmation from the business |  | Robin G |  | NA
S.No. | Attendee | Role | Responsibilities |  |  |  |  | Notes
1 | Pat Flynn | Subject Matter Expert | SPOC for all domain related clarifications and detailing |  |  |  |  | pflynn@acmecorp.com
2 | Jacob Wess | Subject Matter Expert | SPOC for all domain related clarifications and detailing |  |  |  |  | jwess@acmecorp.com
3 | Robin Gupta | Business Analyst | Gather detailed requirements, document and validate scope |  |  |  |  | rgupta@rcube.com
4 | Bill Nelson | Development – Lead | Ensure technical feasibility of the business solution |  |  |  |  | bnelson@rcube.com
5 | Shivank A | Quality/Testing | Plan, design and execute System and Performance testing |  |  |  |  | saggarwal@rcube.com
Note on B9: This column elaborates the purpose of the meeting
Note on C13: Contains the listing of the items to be discussed in the meeting
Note on F13: Contains the outcome that is desired from the respective action item
Note on I13: Contains the name of the attendee that is expected to present the action item
Note on K13: Discussion timeframe (in minutes) allotted to the action item for the meeting
Note on L13: Any special notes or comments against the agenda item
Note on C20: Contains names of the attendees invited for the meeting
Note on E20: Contains the specific role of the attendee
Note on F20: Contains the responsibilities expected to be fulfilled by the attendee
Note on L20: Any special notes or comments against the attendee

## Meeting Minutes
MEETING MINUTES
Project Name | Professional Evaluation Application (PEA) |  | Customer |  | Acme Corp.
Meeting Title | Requirement Clarification Discussion |  | Meeting Date |  | Monday, 31 Jan 2022 10:30 AM EST
Meeting Time | 10:30 AM EST |  | Venue |  | Online/WebEx
Attendees | Pat Flynn, Jacob Wess, Robin Gupta, Bill Nelson |  | Absentees |  | Shivank Aggarwal
Minutes
S.No | Agenda Description | Discussion Points |  | Decisions Made
1 | Which roles are supposed to have the permission to create a new assessment? | Discussed about the existing roles available in the application and whether they need the permission to create a new assessment |  | Only 'evaluation panel’ role or the ‘supervisor’ role to have permission to create and edit an assessment
2 | Can the permission to create and edit an assessment assigned/transferred to a new role? | Discussed about the permissions in the application are bounded to the roles and you can only assign/edit roles against a user but not individual permissions |  | No. The permissions to create/edit an assessment are bounded to 'evaluation panel’ role and the ‘supervisor’ roles only
3 | Walkthrough and confirmation of features against 'Assessment Instructions' | Talked about the sequence of tabs while creating a new assessment |  | Assessment Instructions to be the first tab
4 |  | Discussed about the pre-defined instructions and their representation |  | Pre-defined instructions are read-only, cannot be edited by the user and the verbiage for the same have to be given by the Pat/Jacob
5 |  | Discussed and analysed the options to define a new set of instructions for the candidate |  | Define new instructions' option to have a WYSIWYG editor and option for the user to upload a PDF/PPT document containing the instructions
6 | Walkthrough and confirmation of features against 'Assessment Settings' | Discussed about the assessment's Difficulty levels and whether they need to be shown to the candidate |  | Difficulty level will not be shown to the candidate and it’s only for internal purposes
7 |  | Examined the Overall cut-off percentage field |  | This field shall accept only numerical values till 100 as well as decimal values (up to 2 decimal places)
8 |  | Examined the Overall completion time field |  | User can enter the completion time in hours as well as minutes but no decimal values are allowed
9 |  | Examined the Assessment level field |  | This field is not to be shown to the candidate. The options available for selection are: ‘Fresher’, ‘Junior’, ‘Experienced’, ‘Manager’, ‘Senior Manager’ and ‘Leadership’
10 | Walkthrough and confirmation of features against 'Assessment Sections' | Discussed about how a user will create different assessment sections and the options available |  | Maximum number of sub sections within an assessment will be 9.
11 |  | Examined the sub section weightage field |  | The weightage of all the sub sections put together should add up to 100%.
12 | Walkthrough and confirmation of features against 'Assessment Questions' | Discussed about the functionality of selecting existing questions and importing them into the current assessment |  | The population of existing questions should be based on the skill selected by the user. Each of the populated question should have a checkbox beside them allowing the user to import them into the current assessment
13 |  | Discussed about the representation of questions types so that the assessment panel/administrator role can define a question as well as submit the correct answer (for automatic evaluation by the system)
14 |  | Discussed about the 'Drop down' question type |  | System shall show three text boxes namely: Question Statement: Allows user to define the text of the question Question Options: Allows user to define the different options available (separated by comma) as an answer to the question Answer: Contains the correct answer to the question
15 |  | Discussed about the 'Multiple choice, single answer' question type |  | System shall show three text boxes namely: Question Statement: Allows user to define the text of the question Question Options: Allows user to define the different options available (separated by comma) as an answer to the question Answer: Contains the correct answer to the question
16 |  | Discussed about the 'Multiple choice, multiple answer' question type |  | System shall show three text boxes namely: Question Statement: Allows user to define the text of the question Question Options: Allows user to define the different options available (separated by comma) as an answer to the question Answer: Contains the correct answers (separated by comma) to the question
17 |  | Discussed about the 'Fill in the blank, drag and drop' question type |  | Decided that this feature is to be implemented in the next phase of the project owing
18 |  | Discussed about the 'Fill in the blank, drop down' question type |  | Decided that this feature is to be implemented in the next phase of the project
19 |  | Discussed about the 'Reorder' question type |  | Technical team to evaluate the complexity in implementing this question type
20 |  | Discussed about the functionality to add customized scoring to questions |  | By default, each question should be of one point. However, if the user wishes, she/he can customize the scoring. Scores can be given only as whole numbers and not in decimals
21 |  | Discussed about the functionality to delete a question |  | System should ask for a confirmation before deleting a question. However, a question once deleted cannot be recovered

## Action Items
ACTION ITEMS
S.No. | Action Item | Responsibility | Deadline | Current Status | Closure Date | Reasons for delay/Remarks
1 | To provide the verbiage for the pre-defined instructions | Pat Flynn, Jacob Wess | 2022-02-01 | Closed | 2022-02-01
2 | To create the use case document based on the decisions made and submit for a review | Robin | 2022-02-03 | In-progress
3 | To communicate the removal of the 'Fill in the blank, drag and drop' and 'Fill in the blank, drop down' question type from the project scope, to the complete project team | Robin | 2022-02-07 | Open
4 | To change the Functionality Matrix and BRD and document the removal of 'Fill in the blank, drag and drop' and 'Fill in the blank, drop down' question types from the current project scope | Robin | 2022-02-08 | Open
5 | Evaluate the complexity in implementing the 'Reorder' question type | Bill Nelson | 2022-02-10 | In-progress |  | The technical team is doing a POC in order to correctly evaluate the development effort required
Note on C5: Contains the description of the action item
Note on G5: Contains the stakeholder's name whose responsibility is to close the action item
Note on H5: Contains the deadline to complete the action item (date or no. of days)
Note on I5: Contains the current status of the action item (to be selected from the dropdown)
Note on K5: If closed, this column contains the specific date on which the action item was closed
Note on L5: In case the action item is not closed by the specific deadline, this column contains the reason