## Version Details
DOCUMENT VERSIONING DETAILS
Document Name | PEA_Ext_431_Discussion Tracking Document
Project Name | Professional Evaluation Application
Project Code | PEA_Ext_431
Version Number | Change Description | Created/Modified by | Approved by | Date
0.1 | Added the discussion logs for the meeting | Robin G |  | 2022-01-14
Note on B8: Contains the versioning details of the document
Note on C8: Contains details of whether the information was added, deleted or modified in the document
Note on E8: Contains the full name of the user who created, updated or modified the details
Note on F8: Contains the full name of the user who approved the details
Note on G8: Contains the date on which the details were approved. However, if the information is yet to be approved, it should contain the date on which information was created/modified

## Discusssion Tracking Log
DISCUSSION TRACKING LOG
Project Name | Professional Evaluation Application |  |  | Customer | Acme Corp.
Project Code | PEA |  |  | Project Manager | Raj Mathur
Department | IT |  |  | Client SPOC | Pat Flyn, Jacob Wess
Functionality | Discussion Mode | Date | Stakeholders | Discussion/Review Comments | Notes | Status | Closure Date | Document updated?
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The platform will run a batch job that will export a file containing the list of all the candidates with whom the assessment is shared | These details are yet to be discussed with the technical design team | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The exported report should be in a .csv format | These details are yet to be discussed with the technical design team | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The report should contain the name of the assessment given by the candidate |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The report should contain the cut-off % of that assessment |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The report should contain the details of whether the candidate attempted the assessment |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The report should tell whether the candidate passed/failed the assessment |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The report will be sent on the email ID of the person who is registered as an Acme's supervisor on the PEA |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The frequency of this report should be weekly once |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The Supervisor should get the report every Monday morning by 10 AM EST |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | All the reports should be saved in a repository and if required, the system should be able to export the historical reports as well |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The code should be modular and if- required, system should be able to change the report frequency |  | In-progress |  | No
Reports | Meeting | 13/1/2022 | Robin G, Pat Flynn and Jacob Wess | The name of the report file should be PEA_Candidate Weekly Status_mm/dd/yy |  | In-progress |  | No
Note on B9: Contains user Story/use case Name, document name or any other identifier for the discussion
Note on C9: Contains details of mode of the discussion (to be selected from the dropdown)
Note on D9: Contains the date of the discussion
Note on E9: Name and details of the discussion participants
Note on F9: Contains the actual conversations, decisions and review comments
Note on G9: Contains notes or informal comments that the BA/analyst would like to mention against the discussions
Note on H9: Contains the current status of the discussion (to be selected from the dropdown)
Note on I9: Contains the closure date of a discussion (if its status is Closed)
Note on J9: Contains details of whether the respective requirement document (against the discussion) is updated as per the discussion?