## Version Details
Document Versioning Details
Document Name | PEA_Ext_431_Change Control Log
Project Name | Professional Evaluation Application (PEA)
Project Code | PEA_Ext_431
Version Number | Change Description | Created/Modified by | Approved by | Date
0.1 | First draft of the change control log | Robin Gupta |  | 2022-01-20
0.2 | Added details against request no. 001 | Robin Gupta |  | 2022-01-24
Note on B8: Contains the versioning details of the document
Note on C8: Contains details of whether the information was added, deleted or modified in the document
Note on E8: Contains the full name of the user who created, updated or modified the details
Note on F8: Contains the full name of the user who approved the details
Note on G8: Contains the date on which the details were approved. However, if the information is yet to be approved, it should contain the date on which information was created/modified

## Change Control Log
CHANGE CONTROL LOG
Project Name |  | Professional Evaluation Application (PEA) |  |  | Client |  |  | Acme Corp.
Project Code |  | PEA_Ext_431 |  |  | Project Manager |  |  | Raj Mathur
Department |  | Enterprise Solutions |  |  | Client SPOC |  |  | Pat Flynn
Request # | Module | Change Request Title | Change Request Description | Requester | Initiator | Initiation Date | Effort |  | Status | Severity | Closure Date |  | Comments
[7 empty] | Planned | Actual |  |  | Target | Actual
001 | Candidate | Functionality for the candidate to capture a self snapshot before attempting the assessment | The system should carry out the following changes to prevent unscrupulous activities: 1. While sending the assessment invitation, add a note that devices with cameras should be used for taking the assessment. 2. Append an additional step for candidate to capture a self snapshot through the device camera before attempting the assessment - this is a mandatory step 3. The HR and Admin should be able to view the snapshot uploaded by the candidate | Acme Corp. | Robin Gupta |  | 75 man hours |  | Under Discussion | High |  |  | In case the candidate is taking the assessment on a device which does not contain a camera or has a webcam attached, the system should show an alert and not allow the candidate to proceed further
Note on B10: Contains the unique identifier of the change (CR number in the Change Request form)
Note on C10: Contains the name of the module to which the requirement in the change request belongs
Note on D10: Contains the title of the change request
Note on E10: Contains detailed description of the change
Note on F10: Contains the name of the stakeholder who has requested the change
Note on G10: Contains the name of the stakeholder who has initiated the change (on behalf of the requester)
Note on H10: Contains the date on which the change request was initiated
Note on K10: Depicts the current status of the change request
Note on L10: Contains the level of impact of the change
Note on O10: Contains notes, justifications of why the change requests was rejected or any other useful information
Note on I11: Effort estimated before the change request implementation started (in man-days or man-hours)
Note on J11: Actual effort spent on the implementation of the change request (in man-days or man-hours)
Note on M11: Contains the date on which change request implementation is planned to be finished
Note on N11: Contains the date on which change request implementation actually finished